## Sheet1
				V2.2.0					V2.3.0					V2.4.0

				Spring 22				Summer 22				Fall 22				Spring 23				Summer 23				Fall 23				Spring 24				Summer 24				Fall 24
		Owner	Priority	J	F	M	A	M	J	J	A	S	O	N	D	J	F	M	A	M	J	J	A	S	O	N	D	J	F	M	A	M	J	J	A	S	O	N	D
Goal 1: Expand PYroMat
	1.1: Transport/viscosity in ideal gas	Martin	Medium
	1.2: Ideal solids and liquids	Martin	Low
	1.3: More multi-phase substances	Martin	High
	1.4: New types of multi-phase	Martin	Medium
	1.5: Expanded apps module	Martin	Mixed
	1.6: Add new properties	Martin	High
	1.7: Validation	Ranalli/Martin	High
	1.8: Detailed JANAF ig model	Martin	Low

Goal 2: Pedagogical Materials
	2.0: Establish a template/medium	ALL	High
	2.1: Introductory tutorial	Ranalli	High
	2.2: Construct a list of materials	All	High
	… Author materials …	Moore/Ranalli	Medium

Goal 3: Local GUI
	3.0: Design criteria	ALL	High
	3.1: Identify platform	Martin/Ranalli	High
	3.2: Prototype	Ranalli/Martin	High
	3.3: Test with users	Moore/Ranalli	Medium
	3.4: Improve	Ranalli/Martin	Medium
	3.5: Package and release	Martin	High

Goal 4: Web GUI
	4.0: Design criteria	ALL	High
	4.1: Prototype	Ranalli/Martin	High
	4.2: Re-evaluate AWS hosting	Martin	Medium
	4.3: Test with users	Ranalli/Moore	Medium
	4.4: Improve	Ranalli	Medium
	4.5: Package and release	Martin	High

			Martin
			Ranalli
			Moore
			Shared