## Sheet1
				V2.2.0					V2.3.0					V2.4.0

				Spring 22				Summer 22				Fall 22				Spring 23				Summer 23				Fall 23				Spring 24				Summer 24				Fall 24
		Owner	Priority	J	F	M	A	M	J	J	A	S	O	N	D	J	F	M	A	M	J	J	A	S	O	N	D	J	F	M	A	M	J	J	A	S	O	N	D
Goal 1: Expand PYroMat
	1.1: Transport/viscosity in ideal gas	Martin	Medium
	1.2: Ideal solids and liquids	Martin	Low
	1.3: More multi-phase substances	Martin	High
	1.4: New types of multi-phase	Martin	Medium
	1.5: Expanded apps module	Martin	Mixed
	1.6: Add new properties	Martin	High
	1.7: Validation	Martin	High
	1.8: Detailed JANAF ig model	Martin	Low

Goal 2: Pedagogical Materials
	2.0: Establish a template/medium	ALL	High
	2.1: Introductory tutorial for Python users	Martin	High
	2.2: Construct a list of materials	All	High
	2.3: Author pedagogical materials	Moore	High

Goal 3: GUI
	3.1: Survey	ALL	High
	3.2: Criteria	ALL	High
	3.3: Re-evaluate AWS	Martin	High
	3.4: Select GUI platform	Ranalli+Martin	High
	3.5: Prototype GUI	Ranalli	High
	3.6: Transition server	Martin	High
	3.7: Evaluate the prototype	Ranalli	Medium
	3.8: Develop phase I GUI suite	Ranalli	High
	3.9: Release the GUI	Ranalli	High
	3.10: Develop phase II GUI suite	Ranalli	Medium
	3.11: Release phase II GUI suite	Ranalli	Medium

Goal 4: Promote and publish
	4.1: About article in OLS or OSS journal	ALL
	4.2: Pedagogical article	ALL
	4.3 Two additional papers	ALL
	4.4: Pycon	Martin + ?

			Martin
			Ranalli
			Moore
			Shared